## Team
Initials | First_Name | Last_Name | Email_Id | Github_Username
ng | Nancy | Gupta | ngupta19@stevens.edu | NancyGuptaEr
pr | Poorvi | Raut | praut1@stevems.edu | praut14
rd | Riya | Divakaran | rdivakar@stevens.edu | rdivakar31
pk | Pramod Kumar | Kanigiri | pkanigir@stevens.edu | pramod1109
GithubRepository - CS555_Agile_Team04_Fall2023

## Sprint_01
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | DivorceDate before current date | ng | Completed | 100 | 120 | 80 | 100 | YES
US02 | Birth before marriage | ng | Completed | 70 | 180 | 32 | 90 | YES
US03 | Birth before death of parents | pr | Completed | 100 | 110 | 70 | 100 | YES
Us04 | List upcoming birthdays | pr | Completed | 70 | 170 | 30 | 70 | YES
US05 | Unique families by spouses | pk | Completed | 100 | 120 | 33 | 70 | YES
US06 | Unique first names in families | pk | Completed | 70 | 150 | 32 | 80 | YES
Us07 | Check for Divorce and Remarriage | rd | Completed | 100 | 110 | 80 | 100 | YES
Us08 | Check for Death and Remarriage | rd | Completed | 70 | 150 | 33 | 80 | YES
Avoid:
| Review Results |  |  |  |  | Don't wait till the last moment
| Completed Sprint_1 successfully |  |  |  |  | Prioritise userstories as per customer requirements
Working as a team
Tested using various methods
Updated Burndown Chart
User stories for Sprint_2 decided

## Sprint_02
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US09 | Less than 150 years old | ng | Pending | 100 | 60 | 30 | 40 | YES
US10 | Birth before death | ng | Pending | 120 | 95 | 20 | 20 | YES
US11 | Number of divorces in the family | pr | Pending | 100 | 110 | 33 | 80 | YES
US12 | Unique last names in the family | pr | Pending | 70 | 150 | 28 | 100 | YES
US13 | Detect multiple births on same day | rd | Pending | 100 | 80 | 30 | 20 | YES
US14 | Age difference between spouses | rd | Pending | 110 | 70 | 22 | 80 | YES
US15 | list individuals with multiple marriages | pk | Pending | 100 | 120 | 35 | 80 | YES
US16 | identify orphans. | pk | Pending | 70 | 110 | 32 | 70 | YES
Sprint_02 Review Results
Working together as a team
Team keeping up the pace
Prioritised which stories to implement first
Decided which user stories to do for Sprint_2
Avoid:
Don't delay urgent deliverables

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | DivorceDate before current date | ng | Completed
1 | US02 | Birth before marriage | ng | Completed
1 | US03 | Birth before death of parents | pr | Completed
1 | US04 | List upcoming birthdays | pr | Completed
1 | US05 | Unique families by spouses | pk | Completed
1 | US06 | Unique first names in families | pk | Completed
1 | US07 | Check for Divorce and Remarriage | rd | Completed
1 | US08 | Check for Death and Remarriage | rd | Completed
2 | US09 | Less than 150 years old | ng | Pending
2 | US10 | Birth before death | ng | Pending
2 | US11 | Number of divorces in the family | pr | Pending
2 | US12 | Unique last names in the family | pr | Pending
2 | US13 | Detect multiple births on same day | rd | Pending
2 | US14 | Age difference between spouses | rd | Pending
2 | Us15 | list individuals with multiple marriages | pk | Pending
2 | Us16 | identify orphans. | pk | Pending
3 | US17 | List living married | ng | Pending
3 | US18 | Siblings spacing | ng | Pending
3 | US19 | working individuals | pr | Pending
3 | US20 | list of dependents in family | pr | Pending
3 | US21 | Calculate Generations | pk | Pending
3 | US22 | List Adopted Children | pk | Pending
3 | US23 | List Siblings with Large Age Differences | rd | Pending
3 | US24 | List Multiple Marriages of Individuals | rd | Pending

## Burndown
Date | Remaining Stories | Story Velocity | Lines Of Code | Min | Code Velocity
2023-09-18 | 32 |  | 0
2023-10-02 | 24 | 8 | 230 | 32 | 115

## Burndown_readme
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2023-09-18 | 32 |  | 0
Sprint 1 | 2023-10-02 | 16 | 16 | 230 | 32 | 115
Sprint 2 | 2023-10-16
Sprint 3 | 2023-10-30
Sprint 4 | 2023-11-13
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories